## Sheet1
Product Backlog
Name | Description | Time (estimated hours) | Implemented Yet?
Planet Model | Find a way to make a 3D model of all the planets we want to implement | 2 | Yes
Planet Class | Create a general planet class that handles creating all the specific planets. | 10 | Yes
Music | Different music plays when the user "visits" a planet | 15 | A little bit
Universe | A universe class that holds all the planets and manages the camera. | 20 | Yes
User Input | Handles everything the user wants to do within the program | 15 | No
Physics | Shows accurate physics, such as the roation and oribit time, how the sun interacts with the planets, etc | 10 | No
Server | Setting up a web server so it can be accessed on the web | 5 | Yes
Synthesizer | Making a synthesizer so our own music can be made without the problems of copyright. | 5 | A little bit